## Sheet1
Task | Estimated Time to Complete
Set up BLOC and trigger transitions between states | 30 minutes
Create a melee and ranged enemy | 1 hour
Create a parent bulet class and two other classes bullet classes - player and enemy, that inherite from it | 40 minutes
Create a spawner class that randomly spawns one of the two types of enemies | 2 hours
Create the hud | 1 hour
Create a gun class. The gun is going to rotate around the player with some offset | 1 hour and 30 minutes
Create a pool class for the pooling pattern and implement it | 45 minutes
Create some upgrades on level up | 1 hour
Total time: | 8 hours and 25